## PTD - Failing project costs
HOW MUCH DOES A PROJECT REALLY COST?
We have created this ROI Spreadsheet to help you calculate the real cost of a project that is stuck or failing. Simply complete the cells in pale green, these will then auto calculate in to the darker and solid green cells to calculate the cost. (An example has been created for you to amend to your own figures)
2000000 | Box 1 | Original planned business benefit
This is the value you were expected to generate for the business or save by completing this project
DIRECT COSTS
| Box 2 | 5 | Number of people working directly on the project
This should include all people who commit time as part of the project
| Box 3 | 6 | Average number of days each person works a week
This is the average number of days across all project resources - set to 5 working days if all are full time
| Box 4 | 3 | Number of management days per week
This is the number of days for oversight by line managers not assigned to the project
| Box 5 | 14 | Total working days per week (calculated)
| Box 6 | 10 | Number of weeks project has been running
| Box 7 | 140 | Total working days used (calculated)
| Box 8 | 550 | Average cost per day per person
77000 | Box 9 |  | Project people costs
| Box 10 | 60000 | Cost of time & effort stakeholders have spent on project
This is the business cost for time spent by SMEs/stakeholders not assigned directly to the project
| Box 11 | 200000 | Cost of unrealised future business benefit
Expected return or any related future projects that were dependent on this one completing
| Box 12 | 100000 | Cost of planning & starting a replacement project or solution
This is the approx cost of re-starting an alternative project to replace this orignal one
| Box 13 | 10000 | Other costs incurred on this project
This is the total of any other cost - software, hardware, professional advice….
370000 | Box 14 |  | Indirect project costs
447000 | Box 15 |  | Sub Total Direct & Indirect costs (to date)
| Box 16 | 100000 | Value of original scope that can still be delivered
This is the value when original expected return (Box 1) is multiple by the % in Box 16
1453000 |  | Total Cost of non-Delivery